## Sheet1
Title | Description | User | Functional Area | Origin JIRA tickets | Priority | Estimation | Questions/Notes | Dependency | Type | Comments | Assumption: | MVP | Release 3.1
Create new physical inventory schedule and period | As an admin I want to create new physical inventory schedule so that I can assign later | System Admin | Physical Inventory | OLMIS-1145 |  | 5 | UI? Frequency and period | Reference data: schedule | User Story |  | Reference data UI cannot be used
Assign physical inventory schedule to facility type and program | As an admin I want to create new physical inventory schedule so that I can assign later | System Admin | Physical Inventory | OLMIS-1145 | High | 3 | One physical inventory schedule for one facility type and program combination? |  | User Story |  | One
removing mapping physical inventory schedule | As an admin I want to detach assigned physical inventory schedule with facility type and program combination so that I can adapt to new policy | System Admin | Physical Inventory | OLMIS-1145 |  | 3 |  |  | User Story
Delete physical inventory shedule | As an admin I want to remove physical inventory schedule so that I can corret my mistake if it happens | System Admin | Physical Inventory | OLMIS-1145 |  | 3 |  |  | User Story |  | Reference data handle it
Generate due physical inventory notification | As xx I want to receive notification so that I would know when I need to do the physical inventory | xx | Physical Inventory | OLMIS-695 | High | 3 | Who would receive this notification? Define when to trigger the notification and in which way. Notification service will handle the display | Dependency on close-out time, notification service | User Story |  | Assume no need to configure how many days in advace
Ignore/Dimiss the physical inventory notification |  | xx | Physical Inventory | OLMIS-695 |  | N/A | How long will this dismiss last? One day or one period. Notification service handle this |  | User Story |  | Notification service will handle it
Physical Inventory list page | As a storeroom clerk I want to view my physical inventory for a specific program so that I can create an open physical inventory | Storeroom Clerk | Physical Inventory |  |  | 13 | Including program search. |  | User Story | It also set up the physical inventory mode we may need to change event model, right now they are independent, we may need to group them.
New Physical inventory page | As a storeroom clerk I want to fill my physical inventory so that I can record the physical inventory amount | Storeroom Clerk | Physical Inventory | OLMIS-532 | High | 8 |  | Either notification or the homepage, but if it is the first physical inventory page then it is 13 | User Story |  | Pagination? Non stock cards orderable will be listed out? | Y | Y
Save draft physical inventory page |  | Storeroom Clerk | Physical Inventory | OLMIS-532 | High | 8 |  |  | User Story |  | support offline | Y | Y
View one physical inventory page |  | Storeroom Clerk | Physical Inventory |  | High | 5 |  |  | User Story |  |  | Y
Print single physical inventory page |  | Storeroom Clerk | Print |  | High | 5 |  |  | User Story |  | Generating PDF
Submit physical inventory stock |  | Storeroom Clerk | Physical Inventory | OLMIS-532 | High | 3 | Update SOH and create adjustment stock event |  | User Story |  |  | Y | Y
Integating with requisition service: populate data from physical inventory to requisition |  | Storeroom Clerk | Integrartion with Requisition |  | N/A |  |  | User Story |  | Requisition service will handle it
Stock Management Overview/Homepage |  | Storeroom Clerk | Homepage | OLMIS-647 |  | ??? | It could be navigation bar or a single page with different buttons |  | User Story
Multiple select Orderable |  |  |  |  | High | 3 |  |  |  |  | including orderables without stock cards | Y | Y
Program dropdown list- stock management permission |  |  |  |  | High | 3 |  |  |  |  | Home facility supported program | Y | Y
Facility dropdown list-stock management permission |  |  |  |  | High | 3 |  |  |  |  | I select my managed facilities | Y
Choose orderables page: adjustment |  | Storeroom Clerk | Adjustment | OLMIS-19 | High | 5 | Sort, search, multi-selection function. Should allow search facility? If yes, what facilties can be selected? Any orderables can be selected | Homepage or the expiration notification | User Story |  | Homepage or the expiration notification | Y | Y
Make adjustment |  | Storeroom Clerk | Adjustment | OLMIS-19 | High | 8 | Quantity, date validation? |  | User Story | Support Lot UI |  | Y | Y
View single stock card |  | Storeroom Clerk | View |  | High | 8 |  | Story template | User Story |  | Report as process data and occurred date selection?Pagination | Y | Y
View SOH summary |  | Storeroom Clerk | View |  | High | 8 |  | Homepage? | User Story |  | Sort, filter, search function. Including both process data and occurred date selection | Y | Y
Print single stock card |  | Storeroom Clerk | Print |  | High | 3 | Download PDF |  |  | If it is not the first print story then it should be 3, otherwise it is 5 |  |  | Y
Issuer view receiver's notification |  | Storeroom Clerk | Receive |  |  | 21 | Not confirm how to do it |  | User Story | Havnt got a confirmed solution yet
Issuer confirm receiver's notification |  | Storeroom Clerk | Receive |  |  | ???? | Not confirm how to do it |  | User Story | Havnt got a confirmed solution yet
Issuer Update receiver's notification |  | Storeroom Clerk | Receive |  |  | ???? | Not sure what will happen |  | User Story | Havnt got a confirmed solution yet
Issuer Reject notification |  | Storeroom Clerk | Receive |  |  | ???? | Not sure what will happen |  | User Story | Havnt got a confirmed solution yet
Initial page for Receive |  | Storeroom Clerk | Receive | OLMIS-634 | High | 5 | Sort, search, multi-selection function. Select source. Should allow search facility? If yes, what facilties can be selected? | Homepage | User Story | Including select orderables, source | Not support lot to be selected but lot information will be displayed on the make issue page
Make receive |  | Storeroom Clerk | Receive | OLMIS-634 | High | 8 |  |  | User Story |  | Support lot
View and input lot information |  | Storeroom Clerk | Lot feature |  |  | 5 | Can I add new lot? | Lot feature | User Story
Review receive stock events |  | Storeroom Clerk | Receive | OLMIS-634 |  | 3 | Update the SOH at front-end |  | User Story
Submit receive stock events |  | Storeroom Clerk | Receive | OLMIS-634 | High | 2 | backend calculation |  | User Story
Genarate/send notification to issuer |  | Storeroom Clerk | Receive |  |  | ???? | When to send that notification and in which way? | Submit receive stock event, close-out date | User Story | Havnt got a confirmed solution yet
Receiver confirm issuer's notification |  | Storeroom Clerk | Receive |  |  | ???? | Auto-create an receive event, assume somehting has been done |  | User Story | Havnt got a confirmed solution yet
Receiver update issuer's notification |  | Storeroom Clerk | Receive |  |  | ???? | Not sure what will happen, something has been done on the issue side |  | User Story | Havnt got a confirmed solution yet
Receiver reject notification |  | Storeroom Clerk | Receive |  |  | ???? | Not sure what will happen |  | User Story | Havnt got a confirmed solution yet
Initial page: Issue |  | Storeroom Clerk | Issue | OLMIS-635 | High | 5 |  | Homepage | User Story |  | Not support lot to be selected but lot information will be displayed on the make issue page
Make issue |  | Storeroom Clerk | Issue | OLMIS-635 | High | 3 |  |  | User Story |  | Support lot
Review issue stock events page |  | Storeroom Clerk | Issue | OLMIS-635 |  | 2 |  |  | User Story
Submit issue stock events |  | Storeroom Clerk | Issue | OLMIS-635 | High | 2 |  |  | User Story
Genarate/send notification to receiver |  | Storeroom Clerk | Issue |  |  | 2 | When to send that notification and in which way? Somehting is done | Submit issue stock event | User Story |  | Notification service will handle it
Receive a POD |  | Storeroom Clerk | Receive | OLMIS-1435 |  | N/A |  |  | User Story |  | Fulfillment service will handle it
View a POD |  | Storeroom Clerk | Receive |  |  | N/A |  |  | User Story |  | Fulfillment service will handle it
Confirm a POD |  | Storeroom Clerk | Receive | OLMIS-615 |  | N/A |  |  | User Story |  | Fulfillment service will handle it
Update a POD |  | Storeroom Clerk | Receive |  |  | N/A |  |  | User Story |  | Fulfillment service will handle it
Reject a POD |  | Storeroom Clerk | Receive |  |  | N/A |  |  | User Story |  | Fulfillment service will handle it
Set up close-out time |  | System Admin | Configuration |  |  | 3 |  |  | User Story |  | may be more than a specific time
Create new reasons |  | System Admin | Configuration |  |  | 2 |  |  | User Story |  |  | Y | Y
Create new organizations |  | System Admin | Configuration |  |  | 2 |  |  | User Story |  |  | Y
Assign reasons |  | System Admin | Configuration |  |  | 3 |  |  | User Story
Assign desinations/sources |  | System Admin | Configuration |  |  | 3 |  |  | User Story
Detach assigned reasnons |  | System Admin | Configuration |  |  | 2 |  |  | User Story |  |  | Y
Detach assigned destination/sources |  | System Admin | Configuration |  |  | 2 |  |  | User Story
Turn on/off lot feature |  | System Admin | Configuration |  | High | 2 |  |  | User Story |  | Only a configuration for system admin | Y
Trigger low stock notification |  | System Admin | Configuration |  |  | 3 | When to trigger it | Minimum stock and close out date | User Story
Trigger stock out notification |  | System Admin | Configuration |  |  | 2 | When receive via what |  | User Story
Define minimum stock level formula |  | System Admin | Configuration | OLMIS-978 |  | 5 |  |  | User Story
Archive reasons |  | System Admin | Configuration |  |  | 3 |  |  | User Story |  |  | Y
Archive organizations |  | System Admin | Configuration |  |  | 3
Handle the archive of reference data: facility, lot, tradeitem... |  | System Admin | Configuration |  |  | 8 | [5 empty] | Y
Create new lot |  | System Admin | Configuration |  | High | N/A |  |  | User Story |  | Reference data service will handle it | Y
Update lot |  | System Admin | Configuration |  |  | N/A |  |  | User Story |  | Reference data service will handle it | Y
Archive lot |  | System Admin | Configuration |  |  | N/A |  |  | User Story |  | Reference data service will handle it
Permission Management |  |  | Configuration |  | High | 8 |  |  | User Story |  | Reference data will handle the rights/role | Y | Y
Caculate AMC |  | Storeroom Clerk | Configuration |  |  | 3 |  |  |  |  | get it from reference data? | Y
Data correction |  | Storeroom Clerk | Data correction |  |  | 13 |  |  |  |  | Two ways to correct data
Using requisition data to create stock event |  | Implementer | Immigration |  |  | 13 | Unsure what to do
Stock Card query interface:commoditytype |  |  | Physical inventory |  | High | 5 |  |  |  |  | GS1 is done in reference data
Stock Card query interface:tradeitem |  |  |  |  | High | 5 |  |  |  |  | GS1 is done in reference data
Stock Card restructure:lot |  |  |  |  | High | 21 |  |  |  | this is end to end impact to all existing stock events/cards/line items. including processing, persisting and reading and recalculating | Assumption: lot information coming from reference data service | Y | Y
Redesign resons | [5 empty] | ????
Stock Management Approval | 1. Add functionality to have an approver sign off on an Audit/Verification. Stores often have monthly/periodic audits - usually around physical stock counts - where a second person approves/verifies the SOH on the system. 2. If an adjustment (damages/expiries/phy stock count, etc.) exceeds certain %, require an explanation or note for why the adjustment was that large. |  |  | OLMIS-1620 |  | ????
Stock Management notification | any SOH update will send out an notification |  |  | OLMIS-1439 |  | ????
[UI] Configure stock card template | This is the UI part |  |  | OLMIS-539 |  | 5
Recall stock |  |  |  | OLMIS-1116 |  | ????
Report recalled stock |  |  |  | OLMIS-1429 |  | ????
Available SOH and SOH | [5 empty] | ????
Update the stock card template if GS1 applies |  |  |  |  | High | 5 |  |  |  | Lot, tradeitem would introduce more fields
Validate negative SOH | [5 empty] | 1 | [5 empty] | Y | Y
Using the current UI tool to build a 'Hello world' page | [5 empty] | ????
Update the table structure of stock event and stock line items | [5 empty] | ????
Configure expiry notification | [5 empty] | 3
Using existing requisition schedule for stock management physical inventory schedule | [5 empty] | 8 | [5 empty] | Y
Print SOH summary | [5 empty] | 2 | [5 empty] | Y | Y
Allow users to create a stock event that issue more than SOH quantity | [5 empty] | ????
Create an order to request | [5 empty] | ????