## Burn-Up
| Iteration | Story Points Completed - Team ILL | Story Points Completed - AYIC/ToP | Story Points Completed - TOTAL | Total Completed | Forecast Completed | Forecast High | Forecast Low | MVP |  | Iteration | Story Points Completed | Total Completed | Forecast Completed | Forecast High | Forecast Low | MVP |  | Iteration | Story Points Completed | Total Completed | Forecast Completed | Forecast High | Forecast Low | MVP |  | Iteration | Story Points Completed | Total Completed | Forecast Completed | Forecast High | Forecast Low | MVP | Evalute for fixed time, variable scope |  | Iteration | Story Points Completed | Total Completed | Forecast Completed | Forecast High | Forecast Low | 3.0
| 10 | 5 | 18 | 23 | [7 empty] | 23 | [7 empty] | 23 | [7 empty] | 23 | [8 empty] | 23
| 11 | 8 | 138 | 146 | [7 empty] | 146 | 0 | [6 empty] | 146 | 0 | [6 empty] | 146 | 0 | [7 empty] | 146 | 0
| 12 | 43 | 124 | 167 | [6 empty] | 12 | 167 | 167 | [5 empty] | 12 | 167 | 167 | [5 empty] | 12 | 167 | 167 | [6 empty] | 12 | 167 | 167 |  |  |  | 965
| 13 | 29 | 150 | 179 | [6 empty] | 13 | 179 | 346 | [5 empty] | 13 | 179 | 346 | [5 empty] | 13 | 179 | 346 | [6 empty] | 13 | 179 | 346 |  |  |  | 965
| 14 | 25 | 124 | 149 | [6 empty] | 14 | 149 | 495 | [5 empty] | 14 | 149 | 495 | [5 empty] | 14 | 149 | 495 | [6 empty] | 14 | 149 | 495 |  |  |  | 965
| 15 | 39 | 131 | 170 | [6 empty] | 15 | 170 | 665 | [5 empty] | 15 | 170 | 665 | [5 empty] | 15 | 170 | 665 | [6 empty] | 15 | 170 | 665 |  |  |  | 965
| 16 | 6 | 60 | 66 | [6 empty] | 16 | 66 | 731 | [5 empty] | 16 | 66 | 731 | [5 empty] | 16 | 66 | 731 | [6 empty] | 16 | 66 | 731 |  |  |  | 1790
| 17 | 27 | 116 | 143 | [6 empty] | 17 | 143 | 874 | [5 empty] | 17 | 143 | 874 | [5 empty] | 17 | 143 | 874 | [6 empty] | 17 | 143 | 874 |  |  |  | 1330
| 18 | 48 | 163.5 | 211.5 | [6 empty] | 18 | 211.5 | 1085.5 | [5 empty] | 18 | 211.5 | 1085.5 | [5 empty] | 18 | 211.5 | 1085.5 | [6 empty] | 18 | 211.5 | 1085.5 |  |  |  | 1330
| 19 | 37 | 220.5 | 257.5 | [6 empty] | 19 | 257.5 | 1343 | [5 empty] | 19 | 257.5 | 1343 | [5 empty] | 19 | 257.5 | 1343 | [6 empty] | 19 | 257.5 | 1343 |  |  |  | 1330
| 20 | 16 | 216.5 | 232.5 | [6 empty] | 20 | 232.5 | 1575.5 | [5 empty] | 20 | 232.5 | 1575.5 | 1575.5 |  |  |  |  | 20 | 232.5 | 1575.5 | 1575.5 | 1575.5 | 1575.5 |  |  |  | 20 | 232.5 | 1575.5 | 1575.5 | 1575.5 | 1575.5 | 1330
Forecast | [9 empty] | Forecast | [7 empty] | Forecast |  |  |  | 1809.3333 |  |  |  | Forecast |  |  |  | 1809.3333 | 1832.3623 | 1786.3044 |  |  | Forecast |  |  |  | 1809.3333 | 1832.3623 | 1786.3044 | 1330
[22 empty] | 2043.1667 | [7 empty] | 2043.1667 | 2089.2246 | 1997.1087 | [6 empty] | 2043.1667 | 2089.2246 | 1997.1087 | 1330
|  |  |  | Average Points Completed Last 3 Sprints: | [7 empty] | Average Points Completed Last 3 Sprints: | [7 empty] | Average Points Completed Last 3 Sprints: |  |  |  | 233.8333 |  |  |  | Average Points Completed Last 3 Sprints: |  |  |  | 233.8333 |  |  |  |  | Average Points Completed Last 3 Sprints: |  |  |  | 233.8333
|  |  |  | Standard Deviation Points Last 3 Sprints | [7 empty] | Standard Deviation Points Last 3 Sprints | [7 empty] | Standard Deviation Points Last 3 Sprints | [7 empty] | Standard Deviation Points Last 3 Sprints |  |  |  | 23.029 |  |  |  |  | Standard Deviation Points Last 3 Sprints |  |  |  | 23.029
Velocity over time | [9 empty] | Sum velocity over time and plot | [7 empty] | Add a forecast | [7 empty] | Add forecast highs and lows | [8 empty] | Evaluate for fixed scope, variable time

## Epics
Epic | Link | OriginalEpicSize | Orig. Points | RevisedEpicSize | Revised Points | Notes
Requisition UI | https://openlmis.atlassian.net/issues/?jql=%22Epic%20Link%22%20%3DOLMIS-1022%20and%20status!%3DDead%20order%20by%20fixVersion%20ASC%2C%20status%20DESC%2C%20updated%20ASC | Medium | 55 | Medium | 130
Reference UI Module | https://openlmis.atlassian.net/issues/?jql=%22Epic%20Link%22%20%3DOLMIS-38%20and%20status!%3DDead%20and%20fixVersion%3D3.0%20%20order%20by%20fixVersion%20ASC%2C%20status%20DESC%2C%20updated%20ASC | Medium | 55 | Medium | 130
UI Extensibility | https://openlmis.atlassian.net/issues/?jql=%22Epic%20Link%22%3DOLMIS-1510%20and%20status!%3DDead%20and%20fixVersion%3D3.0%20order%20by%20fixVersion%20ASC%2C%20status%20DESC%2C%20updated%20ASC |  |  |  |  | just 2 tickets; didn't have any original size or points
Offline Requisitions | https://openlmis.atlassian.net/issues/?jql=%22Epic%20Link%22%20%3DOLMIS-572%20and%20status!%3DDead%20order%20by%20fixVersion%20ASC%2C%20status%20DESC%2C%20updated%20ASC | Small-Medium | 20 | Small-Medium | 50
Requisition Improvements | https://openlmis.atlassian.net/issues/?jql=%22Epic%20Link%22%20%3DOLMIS-1250%20and%20status!%3DDead%20order%20by%20fixVersion%20ASC%2C%20status%20DESC%2C%20updated%20ASC | Large | 90 | Large | 210
Requisition template 3.0 | https://openlmis.atlassian.net/issues/?jql=%22Epic%20Link%22%20%3DOLMIS-1065%20and%20status!%3DDead%20order%20by%20fixVersion%20ASC%2C%20status%20DESC%2C%20updated%20ASC | Medium | 55 | Medium | 130
Reference data refactoring | https://openlmis.atlassian.net/issues/?jql=%22Epic%20Link%22%20%3DOLMIS-566%20and%20status!%3DDead%20order%20by%20fixVersion%20ASC%2C%20status%20DESC%2C%20updated%20ASC | Medium | 55 | Medium | 130
Upload Reference Data | https://openlmis.atlassian.net/issues/?jql=%22Epic%20Link%22%20%3DOLMIS-1302%20and%20status!%3DDead%20order%20by%20fixVersion%20ASC%2C%20status%20DESC%2C%20updated%20ASC | Medium | 55 |  |  | removed from 3.0 scope
Order Export | https://openlmis.atlassian.net/issues/?jql=%22Epic%20Link%22%20%3DOLMIS-639%20and%20status!%3DDead%20and%20fixVersion%3D3.0%20order%20by%20fixVersion%20ASC%2C%20status%20DESC%2C%20updated%20ASC | Small-Medium | 20 | Small-Medium | 50
Orders 3.0 | https://openlmis.atlassian.net/issues/?jql=%22Epic%20Link%22%20%3DOLMIS-1548%20and%20status!%3DDead%20and%20fixVersion%3D3.0%20order%20by%20fixVersion%20ASC%2C%20status%20DESC%2C%20updated%20ASC |  |  |  |  | just 3 UI tickets; didn't have any original size or points
Electronic Stock Card | https://openlmis.atlassian.net/issues/?jql=%22Epic%20Link%22%20%3DOLMIS-623%20and%20status!%3DDead%20and%20fixVersion%3D3.0%20order%20by%20fixVersion%20ASC%2C%20status%20DESC%2C%20updated%20ASC | Medium | 55 | Medium | 130
Receiving Process | https://openlmis.atlassian.net/browse/OLMIS-646 | Small | 15 |  |  | removed from 3.0 scope
Shipment from external ERP | https://openlmis.atlassian.net/issues/?jql=%22Epic%20Link%22%20%3DOLMIS-644%20and%20status!%3DDead%20order%20by%20fixVersion%20ASC%2C%20status%20DESC%2C%20updated%20ASC | Small | 15 |  |  | removed from 3.0 scope
Local Fulfillment | https://openlmis.atlassian.net/issues/?jql=%22Epic%20Link%22%20%3DOLMIS-208%20and%20status!%3DDead%20and%20fixVersion%3D3.0%20%20order%20by%20fixVersion%20ASC%2C%20status%20DESC%2C%20updated%20ASC | Medium | 55 |  |  | removed from 3.0 scope
Budgeting Feature | https://openlmis.atlassian.net/issues/?jql=%22Epic%20Link%22%20%3DOLMIS-1090%20and%20status!%3DDead%20order%20by%20fixVersion%20ASC%2C%20status%20DESC%2C%20updated%20ASC | Small-Medium | 20 |  |  | removed from 3.0 scope
Configurable Notification Service | https://openlmis.atlassian.net/issues/?jql=%22Epic%20Link%22%20%3DOLMIS-1094%20and%20status!%3DDead%20order%20by%20fixVersion%20ASC%2C%20status%20DESC%2C%20updated%20ASC | Medium | 55 | Small | 30 | priority is Email notifications for 3.0 scope
System Administration | https://openlmis.atlassian.net/issues/?jql=%22Epic%20Link%22%20%3DOLMIS-692%20and%20status!%3DDead%20order%20by%20fixVersion%20ASC%2C%20status%20DESC%2C%20updated%20ASC | Medium | 55 |  |  | just 1 ticket for 3.0 scope (negligible epic size)
Program Data | https://openlmis.atlassian.net/issues/?jql=%22Epic%20Link%22%20%3DOLMIS-549%20and%20status!%3DDead%20order%20by%20fixVersion%20ASC%2C%20status%20DESC%2C%20updated%20ASC | Medium | 55 |  |  | removed from 3.0 scope
Jasper Report Framework | https://openlmis.atlassian.net/issues/?jql=%22Epic%20Link%22%20%3DOLMIS-567%20and%20status!%3DDead%20order%20by%20fixVersion%20ASC%2C%20status%20DESC%2C%20updated%20ASC | Medium | 55 | Small | 30 | reducing scope to a single report for v3.0
Modular Architecture and Extension Framework | https://openlmis.atlassian.net/issues/?jql=%22Epic%20Link%22%20%3DOLMIS-1253%20and%20status!%3DDead%20order%20by%20fixVersion%20ASC%2C%20status%20DESC%2C%20updated%20ASC | Medium | 55 | Medium | 130
Dev & Build Infrastructure | https://openlmis.atlassian.net/issues/?jql=%22Epic%20Link%22%20%3DOLMIS-584%20and%20status!%3DDead%20and%20fixVersion%3D3.0%20order%20by%20fixVersion%20ASC%2C%20status%20DESC%2C%20updated%20ASC | Large | 90 | Medium | 130 | Moved most tickets into TechBacklog; the Epic now contains just one story.
Contract tests | https://openlmis.atlassian.net/issues/?jql=%22Epic%20Link%22%20%3DOLMIS-1012%20and%20status!%3DDead%20order%20by%20fixVersion%20ASC%2C%20status%20DESC%2C%20updated%20ASC | Small-Medium | 20 | Small-Medium | 50
GS1 Support | https://openlmis.atlassian.net/issues/?jql=%22Epic%20Link%22%20%3DOLMIS-617%20and%20status!%3DDead%20order%20by%20fixVersion%20ASC%2C%20status%20DESC%2C%20updated%20ASC | Small | 15 |  |  | No longer an epic; just one documentation task.
Total: |  |  | 965 |  | 1330
Data source: http://boardthing.com/board/584753a640097de800000398

## OriginalEpics
Epic | Status | TicketCount3.0 | TicketStoryPoints3.0 | EpicPoints | EpicSize | NewEpicStoryPoints
User Auth. & Password Management | Done | 6 | 18 |  | Small | 15
Configuration & Reference Data | Done | 13 | 37 |  | Medium-Small | 35
Orders (PoD) | Done | 8 | 42 |  | Medium-Small | 35
Upload Reference Data | ToDo | 28 |  |  | Medium | 55
Modular Architecture and Extension Framework | ToDo | 9 |  |  | Medium | 55
Requisition Improvements | ToDo | 35 |  |  | Large | 90
Configurable Notification Service | ToDo | 6 |  |  | Medium | 55
Budgeting Feature | ToDo | 3 |  |  | Small-Medium | 20
Requisition template 3.0 | InProgress | 14 |  |  | Medium | 55
Requisition UI | InProgress | 9 |  |  | Medium | 55
Contract tests | InProgress | 3+ |  |  | Small-Medium | 20
System Administration | ToDo | 2+ |  |  | Medium | 55
Receiving Process | ToDo | 4 |  | 21 | Small | 15
Shipment from external ERP | ToDo | 2 |  | 13 | Small | 15
Order Export | InProgress | 11 |  | 13 | Small-Medium | 20
Electronic Stock Card | ToDo | 10 | 38 | 24 | Medium | 55
GS1 Support | InProgress | 4 |  |  | Small | 15
Dev & Build Infrastructure | InProgress | 37 |  |  | Large | 90
Offline Requisitions | ToDo | 5 |  |  | Small-Medium | 20
Jasper Report Framework | ToDo |  |  | 30 | Medium | 55
Reference data refactoring | ToDo | 6 | 47 |  | Medium | 55
Program Data | ToDo |  |  |  | Medium | 55
Local Fulfillment | ToDo | 14 |  | 23 | Medium | 55
Reference UI Module | InProgress |  |  |  | Medium | 55
Data source: https://docs.google.com/spreadsheets/d/1iMyGbhDM6ebF8mQgCLv-bT6H7K1AaolnoeDAfy8xfvc/edit#gid=0
Template: http://agilewhys.blogspot.com/2015/03/how-to-create-release-burn-up-chart.html
(This sheet contains the original list of Epics for version 3.0 from the Epic Estimation exercise in Sprint 12. Epics marked Done were part of 3.0 beta.)
Note on E1: These were points assigned to epics during Summer 2016
Note on F1: Sizes were assigned during the epic estimation in Sprint 12.
Note on G1: Points are based on the sizes from the OriginalEpicSizes sheet.

## OriginalEpicSizes
| AvgTicketCount | AvgTicketStoryPoints | AvgEpicStoryPoints | NewEpicStoryPoints
Small | 4 | 18 | 17 | 15
Small-Medium | 6 |  | 13 | 20
Medium-Small | 11 | 40 |  | 35
Medium | 13 | 43 | 26 | 55
Large | 35 |  |  | 90